## Job progress
Atlantic Green DD JOB PROGRESS | [5 empty] | TOTAL BUDGET (INITIAL) | CONSUMPTION | TOTAL DIFF. |  |  | ▼ To be changed by commence date (Important!)
4 |  |  |  |  | Shipyard | 837483.3294 | 0 | 837483.3294 |  | Today | Commence | Duration |  |  | Job commence |  |  |  | Job progress |  |  |  | Today |  |  | Job Completion
[5 empty] | Shore Repair | 0 | 0 | 0 |  | 2026-08-22 | 2026-08-19 | 4 |  | ▼ To be changed by commence date (Important!)
[13 empty] | Month | Aug | [22 empty] | Sep
Job number | Category | Job Description | Vendor | Remark / Job progress (Daily update) | Class remark | Initial budget (A) | Consumption (B) | Difference (A-B) | Start date | End Date | Total duration | Progress days | completion (%) | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15
1.1 | Shipyard | Fixed fire fighting system isolation - to be done by vessel crew | [5 empty] | 0 |  |  | 0 | 0 | 0%
1.2 | Shipyard | Ventilation fan rental fee |  |  |  | 1040 |  | 1040 | 2026-08-22 | 2026-09-02 | 11 | 0 | 0%
1.3 | Shipyard | Initial gas free measurement & certification (on Owner account) |  |  |  | 0 |  | 0 | 2026-08-19 | 2026-08-20 | 1 | 1 | 100%
| Shipyard | Inspection & certification of tank cleaning & gas free conditions |  |  |  | 182 |  | 182 | 2026-08-22 | 2026-09-12 | 21 | 0 | 0%
| Shipyard | Daily gas free inspection by Yard's Safety Officers (Compulsory) |  |  |  | 1560 |  | 1560 | 2026-08-20 | 2026-09-12 | 23 | 2 | 8.696%
1.4 | Shipyard | Erection and removal of gangway for whole repair period |  |  |  | 520 |  | 520 | 2026-08-19 | 2026-09-12 | 24 | 3 | 12.5%
1.5 | Shipyard | Pilotage - arranged by Owner's agency on Owner account |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.6 | Shipyard | Docking / undocking of the vessel (For each operation) |  |  |  | 364 |  | 364 | 2026-06-22 | 2026-09-02 | 72 | 61 | 84.72%
| Shipyard | Shifting to repair berth / outside on departure (For each operation) |  |  |  | 364 |  | 364 |  |  | 0 | 0 | 0%
1.7 | Shipyard | Tug service - arranged by Owner's agency on Owner account |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.8 | Shipyard | Connection & disconnection of the fire line |  |  |  | 93.6 |  | 93.6 | 2026-08-19 | 2026-09-12 | 24 | 3 | 12.5%
| Shipyard | Keeping pressurized water in fire line |  |  |  | 764.4 |  | 764.4 | 2026-08-19 | 2026-09-12 | 24 | 3 | 12.5%
| Shipyard | Laying fire proof fabric for protection during hotworks |  |  |  | 5460 |  | 5460 |  |  | 0 | 0 | 0%
1.9 | Shipyard | Fire watchman (8 hours per man) - Compulsory |  |  |  | 3931.2 |  | 3931.2 | 2026-08-19 | 2026-09-12 | 24 | 3 | 12.5%
| Shipyard | Providing watchmen for security of vessel if required |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.10 | Shipyard | Connection & disconnection of ballast water line |  |  |  | 260 |  | 260 |  |  | 0 | 0 | 0%
| Shipyard | Ballast water supply |  |  |  | 1710 |  | 1710 |  |  | 0 | 0 | 0%
1.11 | Shipyard | Connection & disconnection of fresh water line |  |  |  | 31.2 |  | 31.2 |  |  | 0 | 0 | 0%
| Shipyard | Supply fresh water by truck |  |  |  | 2496 |  | 2496 |  |  | 0 | 0 | 0%
1.12 | Shipyard | Connection and disconnection of cable |  |  |  | 78 |  | 78 | 2026-08-22 | 2026-09-12 | 21 | 0 | 0%
| Shipyard | Provide electric power 440V, 60Hz |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Provide electric power 380V, 50Hz |  |  |  | 30000 |  | 30000 | 2026-08-22 | 2026-09-02 | 11 | 0 | 0%
1.13 | Shipyard | Docking / Undocking operation |  |  |  | 3380 |  | 3380 | 2026-08-22 | 2026-09-02 | 11 | 0 | 0% | bar: 2025-08-22 to 2025-09-02
| Shipyard | Docking days |  |  |  | 13650 |  | 13650 | 2026-08-22 | 2026-09-02 | 11 | 0 | 0%
1.14 | Shipyard | Safe berth - wharfage fee |  |  |  | 3640 |  | 3640 |  |  | 0 | 0 | 0%
1.15 | Shipyard | Connection & disconnection of cooling water line |  |  |  | 93.6 |  | 93.6 | 2026-08-22 | 2026-09-02 | 11 | 0 | 0%
| Shipyard | Providing sea water |  |  |  | 546 |  | 546 | 2026-08-22 | 2026-09-02 | 11 | 0 | 0%
1.16 | Shipyard | Cleaning of all aspects/spaces - free of charge for Shipyard Works |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.17 | Shipyard | Bilge water disposal fee |  |  |  | 1300 |  | 1300 |  |  | 0 | 0 | 0%
| Shipyard | Sludge disposal fee |  |  |  | 2600 |  | 2600 |  |  | 0 | 0 | 0%
| Shipyard | Fixed service price for barge or truck |  |  |  | 832 |  | 832 |  |  | 0 | 0 | 0%
| Shipyard | Garbage disposal daily (1 container up to 1.5m3) |  |  |  | 1146.6 |  | 1146.6 |  |  | 0 | 0 | 0%
1.18 | Shipyard | Connection & disconnection of sewage line |  |  |  | 46.8 |  | 46.8 |  |  | 0 | 0 | 0%
| Shipyard | Discharging sewage |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.19 | Shipyard | Connection and disconnection of compressed air line |  |  |  | 78 |  | 78 |  |  | 0 | 0 | 0%
| Shipyard | Compressed air supply |  |  |  | 1560 |  | 1560 |  |  | 0 | 0 | 0%
1.20 | Shipyard | Dock trial attendance after completion of repairs - free of charge |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.21 | Shipyard | Sea trial attendance after completion of repairs - free of charge |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.22 | Shipyard | Providing internet onboard the vessel - free of charge |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.23 | Shipyard | Superintendent's office - free of charge |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.24 | Shipyard | Supply of one mobile for local usage - free of charge |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.25 | Shipyard | Heavy duty paper/plastic protective sheet on passage way decks |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.26 | Shipyard | Bottom plug - Not quoted in shipyard offer |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.27 | Shipyard | Opening & closing of manholes (up to 400x600mm) |  |  |  | 1664 |  | 1664 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of Y/S manhole gaskets |  |  |  | 728 |  | 728 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of bolt and nuts |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of stainless steel studs |  |  |  | 5200 |  | 5200 |  |  | 0 | 0 | 0%
1.28 | Shipyard | Block arrangement for dock preparation - included above (1.13) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.29 | Shipyard | Dock cleaning - free of charge for Shipyard Works |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.30 | Shipyard | Usage of the Crane (cap. 15 ton) min 1 hour |  |  |  | 5720 |  | 5720 |  |  | 0 | 0 | 0%
1.31 | Shipyard | Forklift service (min 0.5 hour) |  |  |  | 1690 |  | 1690 |  |  | 0 | 0 | 0%
| Shipyard | Cherry picker service (min 0.5 hour) |  |  |  | 27955.2 |  | 27955.2 |  |  | 0 | 0 | 0%
| Shipyard | Cherry picker service for Owner - per machine per shift |  | Cancel | To be utilized for Staging budget | 7280 |  | 7280 |  |  | 0 | 0 | 0%
1.32 | Shipyard | Flood light (1000W) for inspection - per light |  |  |  | 2600 |  | 2600 |  |  | 0 | 0 | 0%
1.33 | Shipyard | Scaffolding outside of vessel |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Scaffolding inside of cargo hold |  |  |  | 14430 |  | 14430 |  |  | 0 | 0 | 0%
| Shipyard | Scaffolding inside of tank and closed region |  |  |  | 1040 |  | 1040 |  |  | 0 | 0 | 0%
| Shipyard | Scaffolding tower type (base area max 6.25m2) |  |  |  | 5460 |  | 5460 |  |  | 0 | 0 | 0%
| Shipyard | Temporary safety handrails - per running meter of wire |  |  |  | 1560 |  | 1560 |  |  | 0 | 0 | 0%
1.34 | Shipyard | Skilled worker - mechanical works (8h shift) |  |  |  | 7917 |  | 7917 |  |  | 0 | 0 | 0%
| Shipyard | Skilled worker - steel, piping works (8h shift) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Un-skilled worker - cleaner, painter (8h shift) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Carpenter works (8h shift) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electrical works (8h shift) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Insulation, ventilation and panel workmanship |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Paint workmanship |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.35 | Shipyard | Veeing out / rewelding - per pass, min 1 meter |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Welding and grinding cracks (max 1m crack) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Welding of rudder - per pass, min 1 meter | Carell |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
1.36 | Shipyard | Ultrasonic thickness measurement (min 250 points) | Carell |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Ultrasonic welding / steel control service | Carell |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
2.1 | Shipyard | Closing of side shell scupper discharges / wooden plugs | Carell |  |  | 416 |  | 416 |  |  | 0 | 0 | 0%
2.2 | Shipyard | Hull paint preparation - chemical removal of oil stains | TBA |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
2.3 | Shipyard | Top Side - HP washing before grit blasting |  |  |  | 975 |  | 975 |  |  | 0 | 0 | 0%
| Shipyard | Top Side - Grit blasting SA 2.0 |  |  |  | 4350 |  | 4350 |  |  | 0 | 0 | 0%
| Shipyard | Top Side - Grit blasting SA 1.0 |  |  |  | 1875 |  | 1875 |  |  | 0 | 0 | 0%
| Shipyard | Top Side - A/C touch up - 1st |  |  |  | 273 |  | 273 |  |  | 0 | 0 | 0%
| Shipyard | Top Side - A/C touch up - 2nd |  |  |  | 312 |  | 312 |  |  | 0 | 0 | 0%
| Shipyard | Top Side - Full coat - 1st |  |  |  | 735 |  | 735 |  |  | 0 | 0 | 0%
| Shipyard | Top Side - Full coat - 2nd |  |  |  | 735 |  | 735 |  |  | 0 | 0 | 0%
| Shipyard | Top Side - FW wash down after 1st touch up |  |  |  | 705 |  | 705 |  |  | 0 | 0 | 0%
| Shipyard | Vertical Side - HP washing before grit blasting |  |  |  | 1547 |  | 1547 |  |  | 0 | 0 | 0%
| Shipyard | Vertical Side - Grit blasting SA 2.0 |  |  |  | 36250 |  | 36250 |  |  | 0 | 0 | 0%
| Shipyard | Vertical Side - Full coat - 1st |  |  |  | 1166.2 |  | 1166.2 |  |  | 0 | 0 | 0%
| Shipyard | Vertical Side - Full coat - 2nd |  |  |  | 1166.2 |  | 1166.2 |  |  | 0 | 0 | 0%
| Shipyard | Vertical Side - Full coat - 3rd |  |  |  | 1166.2 |  | 1166.2 |  |  | 0 | 0 | 0%
| Shipyard | Vertical Side - FW wash down after 1st touch up |  |  |  | 1118.6 |  | 1118.6 |  |  | 0 | 0 | 0%
| Shipyard | Flat Bottom - HP washing before grit blasting |  |  |  | 975 |  | 975 |  |  | 0 | 0 | 0%
| Shipyard | Flat Bottom - Grit blasting SA 2.0 |  |  |  | 24650 |  | 24650 |  |  | 0 | 0 | 0%
| Shipyard | Flat Bottom - Full coat - 1st |  |  |  | 735 |  | 735 |  |  | 0 | 0 | 0%
| Shipyard | Flat Bottom - Full coat - 2nd |  |  |  | 735 |  | 735 |  |  | 0 | 0 | 0%
| Shipyard | Flat Bottom - Full coat - 3rd |  |  |  | 735 |  | 735 |  |  | 0 | 0 | 0%
| Shipyard | Flat Bottom - FW wash down after 1st touch up |  |  |  | 705 |  | 705 |  |  | 0 | 0 | 0%
| Shipyard | Fitting of hull anodes (outside) with Owner supply anodes |  |  |  | 187.2 |  | 187.2 |  |  | 0 | 0 | 0%
2.4 | Shipyard | Painting of Plimsoll, draft marks, vessel and home port names |  |  |  | 676 |  | 676 |  |  | 0 | 0 | 0%
| Shipyard | Boot top line |  |  |  | 589.715 |  | 589.715 |  |  | 0 | 0 | 0%
2.5 | Shipyard | Dismantle & refit bow thruster tunnel gratings, clean, blast, paint |  |  |  | 561.6 |  | 561.6 |  |  | 0 | 0 | 0%
2.5.1 | Shipyard | Dismantle & refit stern thruster tunnel gratings, clean, blast, paint |  |  |  | 561.6 |  | 561.6 |  |  | 0 | 0 | 0%
2.6 | Shipyard | Funnel - 450 bar HPFWJ cleaning |  |  |  | 351 |  | 351 |  |  | 0 | 0 | 0%
| Shipyard | Funnel - Mechanical wire brushing with Power Disc (80%) |  |  |  | 2496 |  | 2496 |  |  | 0 | 0 | 0%
| Shipyard | Funnel - Touch up 1 coat |  |  |  | 171.12 |  | 171.12 |  |  | 0 | 0 | 0%
| Shipyard | Funnel - Final coat 1 coat |  |  |  | 171 |  | 171 |  |  | 0 | 0 | 0%
| Shipyard | Funnel - Scaffolding outside of vessel |  |  |  | 4680 |  | 4680 |  |  | 0 | 0 | 0%
2.7 | Shipyard | Hatch cover - Pressurized fresh water washing (350-450 bar) |  |  |  | 468 |  | 468 |  |  | 0 | 0 | 0%
| Shipyard | Hatch cover - Low pressure fresh water washing |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Hatch cover - Water blasting WJ 2.0 (1000-1500 bar) |  |  |  | 3244.8 |  | 3244.8 |  |  | 0 | 0 | 0%
| Shipyard | Hatch cover - Touch up with O/S paint - 2 coats |  |  |  | 186 |  | 186 |  |  | 0 | 0 | 0%
| Shipyard | Hatch cover - Full coat with O/S paint - 1 coat |  |  |  | 342 |  | 342 |  |  | 0 | 0 | 0%
2.8 | Shipyard | Main Deck - Pressurized fresh water washing |  |  |  | 780 |  | 780 |  |  | 0 | 0 | 0%
| Shipyard | Main Deck - Low pressure fresh water washing |  |  |  | 570 |  | 570 |  |  | 0 | 0 | 0%
| Shipyard | Main Deck - Water blasting WJ 2.0 |  |  |  | 5304 |  | 5304 |  |  | 0 | 0 | 0%
| Shipyard | Main Deck - Touch up with O/S paint - 2 coats |  |  |  | 248 |  | 248 |  |  | 0 | 0 | 0%
| Shipyard | Main Deck - Full coat with O/S paint - 1 coat |  |  |  | 570 |  | 570 |  |  | 0 | 0 | 0%
2.9 | Shipyard | Hatch Coaming Top - Pressurized fresh water washing |  |  |  | 78 |  | 78 |  |  | 0 | 0 | 0%
| Shipyard | Hatch Coaming Top - Grit Blasting to SA 2.0 |  |  |  | 1085 |  | 1085 |  |  | 0 | 0 | 0%
| Shipyard | Hatch Coaming Top - Touch up with O/S paint - 2 coats |  |  |  | 107.198 |  | 107.198 |  |  | 0 | 0 | 0%
| Shipyard | Hatch Coaming Top - Full coat with O/S paint - 1 coat |  |  |  | 57 |  | 57 |  |  | 0 | 0 | 0%
2.10 | Shipyard | Cargo Hold Tank Top - Pressurized fresh water washing |  |  |  | 1146.6 |  | 1146.6 |  |  | 0 | 0 | 0%
| Shipyard | Cargo Hold Tank Top - Grit Blasting to SA 2.0 |  |  |  | 9114 |  | 9114 |  |  | 0 | 0 | 0%
| Shipyard | Cargo Hold Tank Top - Touch up with O/S paint - 2 coats |  |  |  | 911.4 |  | 911.4 |  |  | 0 | 0 | 0%
| Shipyard | Cargo Hold Tank Top - Full coat with O/S paint - 1 coat |  |  |  | 837.9 |  | 837.9 |  |  | 0 | 0 | 0%
2.11 | Shipyard | Accommodation - Pressurized fresh water washing |  |  |  | 936 |  | 936 |  |  | 0 | 0 | 0%
| Shipyard | Accommodation - Water blasting WJ 2.0 |  |  |  | 5304 |  | 5304 |  |  | 0 | 0 | 0%
| Shipyard | Accommodation - Touch up with O/S paint - 2 coats |  |  |  | 459.42 |  | 459.42 |  |  | 0 | 0 | 0%
| Shipyard | Accommodation - Full coat with O/S paint - 1 coat |  |  |  | 684 |  | 684 |  |  | 0 | 0 | 0%
| Shipyard | Staging |  |  |  | 7000 |  | 7000 |  |  | 0 | 0 | 0%
2.12 | Shipyard | WBT - Scaffolding inside of tank and closed region |  |  |  | 624 |  | 624 |  |  | 0 | 0 | 0%
| Shipyard | WBT - Hydro blasting 1000 bar |  |  |  | 2500 |  | 2500 |  |  | 0 | 0 | 0%
| Shipyard | WBT - T/U coat painting - 2 coat |  |  |  | 153.14 |  | 153.14 |  |  | 0 | 0 | 0%
2.13 | Shipyard | Cargo crane columns blasting and painting - Not quoted in shipyard offer |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
2.14 | Shipyard | Wind Breaker - To be quoted after inspection |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
2.15 | Shipyard | Cargo Hold Sides - Pressurized fresh water washing |  |  |  | 1560 |  | 1560 |  |  | 0 | 0 | 0%
| Shipyard | Cargo Hold Sides - Grit Blasting to SA 2.0 (Estimated 4980 m2) |  |  |  | 9300 |  | 9300 |  |  | 0 | 0 | 0%
| Shipyard | Cargo Hold Sides - Touch up with O/S paint - 2 coats |  |  |  | 496 |  | 496 |  |  | 0 | 0 | 0%
| Shipyard | Cargo Hold Sides - Full coat with O/S paint - 1 coat |  |  |  | 1140 |  | 1140 |  |  | 0 | 0 | 0%
| Shipyard | Cargo Hold Sides - Cherry picker service (Estimated 120 shifts) |  |  |  | 1456 |  | 1456 |  |  | 0 | 0 | 0%
2.16 | Shipyard | Chain Locker - Please refer to item 4.2 |  |  |  | 3993.6 |  | 3993.6 |  |  | 0 | 0 | 0%
3.1 | Shipyard | Steel renewal tariff - between 0 - 10 tons |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewal tariff - over 10 tons |  |  |  | 82000 |  | 82000 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 20500 |  | 20500 |  |  | 0 | 0 | 0%
| Shipyard | Light Steel |  |  |  | 8000 |  | 8000 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of flat bar on deck up to 10 kg./m |  |  |  | 10000 |  | 10000 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of angle bar on deck up to 10 kg./m |  |  |  | 4400 |  | 4400 |  |  | 0 | 0 | 0%
3.2 | Shipyard | Replacement of cell guides 150x150x15mm, min 1m (Estimated 500m) |  |  |  | 82500 |  | 82500 |  |  | 0 | 0 | 0%
| Shipyard | Staging |  |  |  | 10000 |  | 10000 |  |  | 0 | 0 | 0%
3.3 | Shipyard | Renewal of rubber channels (L profile) |  |  |  | 11000 |  | 11000 |  |  | 0 | 0 | 0%
| Shipyard | Transportation of hatch covers ashore and back - up to 25 tons |  |  |  | 1895.4 |  | 1895.4 | 2026-08-20 | 2026-08-21 | 1 | 1 | 100% | bar: 2025-08-20 to 2025-08-21
3.4 | Shipyard | Fitting and welding of Lashing Eye |  |  |  | 780 |  | 780 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of single raised ISO sockets with O/S spares |  |  |  | 400 |  | 400 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of double raised ISO sockets with O/S spares |  |  |  | 1320 |  | 1320 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of Cone |  |  |  | 5500 |  | 5500 |  |  | 0 | 0 | 0%
3.5 | Shipyard | Renewal of manhole cover 800x600 (void space) |  |  |  | 4800 |  | 4800 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of manhole cover 600x400 (FOT No2) |  |  |  | 4200 |  | 4200 |  |  | 0 | 0 | 0%
3.6 | Shipyard | Louver ventilator rubber gasket renewal (Y/S) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Louver ventilator soft steel renewal - to be quoted after inspection |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
3.7 | Shipyard | Mushroom vent head - dismantle/transport/refit up to 500mm |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Mushroom vent head - grit blast & paint up to 500mm |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
3.10 | Shipyard | Collapsible frame repair - angle bar renewal (Estimated 50 meters) |  |  |  | 22000 |  | 22000 |  |  | 0 | 0 | 0%
| Shipyard | Renewal of chequered plate/rain drops shape 5/6mm |  |  |  | 9307.5 |  | 9307.5 |  |  | 0 | 0 | 0%
| Shipyard | Renewal Soft Steel on Deck |  |  |  | 8000 |  | 8000 |  |  | 0 | 0 | 0%
3.11 | Shipyard | FOT No3 C DB - Plate AH36 (10.0) 500x1000mm (Estimated 40 kg) |  |  |  | 164 |  | 164 |  |  | 0 | 0 | 0%
| Shipyard | FOT No3 C DB - Insert plate 400x400mm (Estimated 40kg) |  |  |  | 164 |  | 164 |  |  | 0 | 0 | 0%
| Shipyard | FOT No3 C DB - engine room area surcharge 35% |  |  |  | 115.2 |  | 115.2 |  |  | 0 | 0 | 0%
| Shipyard | FOT No3 C DB - high grade steel AH36 surcharge 15% |  |  |  | 49.6 |  | 49.6 |  |  | 0 | 0 | 0%
3.12 | Shipyard | The Port side chain locker the round plate 5970X2000X8 mm to be replaced at the dedicated area and STB chain locker the round plate 5970X1500X8 mm to be replace |  |  |  | 5481.7 |  | 5481.7 |  |  | 0 | 0 | 0%
| Shipyard | Fore/ aft peak, pump room, chain locker, accommodation and engine room to be charged 35% extra |  |  |  | 1925.28 |  | 1925.28 |  |  | 0 | 0 | 0%
3.13 | Shipyard | Traverce Bulkead at FR 43 1/2 (CH N04 / ER) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | STBD side plate 5800X300X9mm to be replace- Estimated 125 kg |  |  |  | 512.5 |  | 512.5 |  |  | 0 | 0 | 0%
| Shipyard | Fore/ aft peak, pump room, chain locker, accommodation and engine room to be charged 35% extra |  |  |  | 180 |  | 180 |  |  | 0 | 0 | 0%
3.14 | Shipyard | Frame 85 (CH 3 / HFO) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | STBD side plate 2800X300X10mm to be replace- Estimated 67 kg |  |  |  | 274.7 |  | 274.7 |  |  | 0 | 0 | 0%
| Shipyard | Fore/ aft peak, pump room, chain locker, accommodation and engine room to be charged 35% extra |  |  |  | 96.48 |  | 96.48 |  |  | 0 | 0 | 0%
3.15 | Shipyard | Traverce bulhead at fr 126 (CH No2 / HFO 1 STBD / PS, Overflow) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | STBD side plate 3800X300X8.5mm to be replaced- 78kg |  |  |  | 319.8 |  | 319.8 |  |  | 0 | 0 | 0%
| Shipyard | Fore/ aft peak, pump room, chain locker, accommodation and engine room to be charged 35% extra |  |  |  | 112.32 |  | 112.32 |  |  | 0 | 0 | 0%
3.16 | Shipyard | WBT No2 PS Web Frame 126, Web frame 144 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 12500X300X9mm to be replaced- Estimated 270 kg |  |  |  | 1107 |  | 1107 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 278.1 |  | 278.1 |  |  | 0 | 0 | 0%
| Shipyard | WBT No2 Stbd Web Frame 126, Web frame 144 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 12500X300X9mm to be replaced- Estimated 270 kg |  |  |  | 1107 |  | 1107 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 278.1 |  | 278.1 |  |  | 0 | 0 | 0%
3.17 | Shipyard | Traverce bulhead at fr 145 (CH No2 / CH No1) |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 2700X300X9mm to be replaced- 58 kg |  |  |  | 237.8 |  | 237.8 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 59.74 |  | 59.74 |  |  | 0 | 0 | 0%
3.18 | Shipyard | Double bottom tank No1 C Web frame No156 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 2700X300X9mm to be replaced- 58 kg |  |  |  | 237.8 |  | 237.8 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 59.74 |  | 59.74 |  |  | 0 | 0 | 0%
3.19 | Shipyard | Double bottom tank No1 C PS Web frame146 -156 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 1700X300X8mm to be replaced & 1900X300X8 to be replaced- 69 kg |  |  |  | 282.9 |  | 282.9 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 71.07 |  | 71.07 |  |  | 0 | 0 | 0%
3.2 | Shipyard | Double bottom tank No1 C STBD Web frame146 -156 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 2700X300X8mm to be replaced - 52 kg |  |  |  | 213.2 |  | 213.2 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 53.56 |  | 53.56 |  |  | 0 | 0 | 0%
3.21 | Shipyard | WBT No1 Stbd Web frame 164 |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 800X300X8mm to be replaced - 41 kg |  |  |  | 168.1 |  | 168.1 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 42.23 |  | 42.23 |  |  | 0 | 0 | 0%
3.21 | Shipyard | Double bottom |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Plate 10000X2700X10mm / 900x900x10 / 900x900x12.5 / 2500X3400X10 / 2900X2800X12.5 / 1600X600X10 / 1400X400X10 / 3100X600X10 / 5400X2900X12.5 / 5400X2800X11mm to be replaced - Estimated 3900 kg |  |  |  | 28023.5 |  | 28023.5 |  |  | 0 | 0 | 0%
| Shipyard | Steel renewals inside tanks (TST or Wing Tanks & DB tank internals), closed regions, Cargo tanks/holds +%25 |  |  |  | 7040.05 |  | 7040.05 |  |  | 0 | 0 | 0%
4.1 | Shipyard | Ranging of anchors & chains, washing, calibration, marking (per side) |  |  |  | 6182 |  | 6182 |  |  | 0 | 0 | 0%
4.2 | Shipyard | Opening up, cleaning & painting of chain locker (up to 2m, O/S paint) |  |  |  | 1622.4 |  | 1622.4 |  |  | 0 | 0 | 0%
4.3 | Shipyard | Windlass - renewal of brake lining O/S - per meter |  |  |  | 1924 |  | 1924 |  |  | 0 | 0 | 0%
4.4 | Shipyard | Mooring winch - renewal of brake lining O/S - per meter |  |  |  | 6136 |  | 6136 |  |  | 0 | 0 | 0%
4.5 | Shipyard | Life boat - Load test only |  |  |  | 2236 |  | 2236 |  |  | 0 | 0 | 0%
4.6 | Shipyard | Rescue boat - Load test only |  |  |  | 2417 |  | 2417 |  |  | 0 | 0 | 0%
4.7 | Shipyard | Provision crane load test - SWL 2T |  |  |  | 260 |  | 260 |  |  | 0 | 0 | 0%
4.8 | Shipyard | Accommodation ladder - remove to workshop & refit |  |  |  | 624 |  | 624 |  |  | 0 | 0 | 0%
| Shipyard | Accommodation ladder load test |  |  |  | 676 |  | 676 |  |  | 0 | 0 | 0%
| Shipyard | Accommodation ladder steps renewal - Al - per step |  |  |  | 400 |  | 400 |  |  | 0 | 0 | 0%
4.11 | Shipyard | Deck valve - butterfly/gate/storm overhaul in situ (Estimated 16 pcs, 1560 mm) |  |  |  | 1372.8 |  | 1372.8 |  |  | 0 | 0 | 0%
4.12 | Shipyard | Fire line pipe Main Deck Bay 34 - DN 125 (5") SCH40 |  |  |  | 314.496 |  | 314.496 |  |  | 0 | 0 | 0%
| Shipyard | PN type flange DN 125 |  |  |  | 174.72 |  | 174.72 |  |  | 0 | 0 | 0%
| Shipyard | Elbow DN 125 |  |  |  | 116.48 |  | 116.48 |  |  | 0 | 0 | 0%
4.13 | Shipyard | CH No.1&2 hydraulic block overhaul with O/S spares |  |  |  | 2912 |  | 2912 |  |  | 0 | 0 | 0%
4.14 | Shipyard | CH No.1 hydraulic cylinders overhaul - 200/125-1375 with O/S spares |  |  |  | 4992 |  | 4992 |  |  | 0 | 0 | 0%
4.14 | Shipyard | CH No.2 hydraulic cylinders overhaul - 300/160-1015 with O/S spares |  |  |  | 4992 |  | 4992 |  |  | 0 | 0 | 0%
4.15 | Shipyard | Galley grease trap fabrication - soft steel renewal |  |  |  | 1600 |  | 1600 |  |  | 0 | 0 | 0%
4.16 | Shipyard | HC rubber replacement |  |  |  | 8158 |  | 8158 |  |  | 0 | 0 | 0%
5.1 | Shipyard | Dismantling and refitting of pitch propeller (per blade) including renewal of owner supply o-ring. |  |  |  | 3077 |  | 3077 |  |  | 0 | 0 | 0%
| Shipyard | Polishing of propeller blades |  |  |  | 936 |  | 936 |  |  | 0 | 0 | 0%
| Shipyard | Dye penetration checking of propeller blades |  |  |  | 338 |  | 338 |  |  | 0 | 0 | 0%
| Shipyard | Removal and refitting of propeller rope guard |  |  |  | 234 |  | 234 | 2026-08-22 | 2026-09-02 | 11 | 0 | 0% | bar: 2025-08-22 to 2025-09-02
| Shipyard | Anode on rope guard renewed by yard material |  |  |  | 62.4 |  | 62.4 |  |  | 0 | 0 | 0%
| Shipyard | Net cutter newly installed on 4 location by yard material (SUS) |  |  |  | 208 |  | 208 |  |  | 0 | 0 | 0%
5.2 | Shipyard | Taking deep gauge measurements |  |  |  | 520 |  | 520 |  |  | 0 | 0 | 0%
| Shipyard | Releasing/refitting hydraulic coupling & withdrawal of tailshaft with CPP hub (shaft dia) |  |  |  | 5382 |  | 5382 |  |  | 0 | 0 | 0%
| Shipyard | Dismantling and refitting owner supply simplex seals.(per set, per outer dia.) |  |  |  | 1404 |  | 1404 |  |  | 0 | 0 | 0%
| Shipyard | Measurements of shaft clearances |  |  |  | 520 |  | 520 |  |  | 0 | 0 | 0%
| Shipyard | Fwd & Aft seal renewed by maker engineer with yard assistance |  |  |  | 754 |  | 754 |  |  | 0 | 0 | 0%
| Shipyard | MPI test of shaft keyway - per service |  |  |  | 286 |  | 286 |  |  | 0 | 0 | 0%
| Shipyard | Polishing of shaft connection bolts (Up to 70X400mm) |  |  |  | 1248 |  | 1248 |  |  | 0 | 0 | 0%
| Shipyard | Machining of chrome liner at workshop |  |  |  | 2184 |  | 2184 |  |  | 0 | 0 | 0%
5.3 | Shipyard | Cutting & rewelding of rudder pintle and rudder stock covers |  |  |  | 280.8 |  | 280.8 |  |  | 0 | 0 | 0%
| Shipyard | Measurement of rudder stock / pintle bush / bearing clearances |  |  |  | 280.8 |  | 280.8 |  |  | 0 | 0 | 0%
| Shipyard | Air test of rudder blade (0.2 kg/cm2) |  |  |  | 312 |  | 312 |  |  | 0 | 0 | 0%
| Shipyard | Dismounting & refitting of rudder drain plug and renewal of gasket |  |  |  | 29.9 |  | 29.9 |  |  | 0 | 0 | 0%
| Shipyard | Dismantling & refitting of rudder blade / kort nozzle |  |  |  | 2059.2 |  | 2059.2 |  |  | 0 | 0 | 0%
5.4 | Shipyard | Removal of gratings, HPWJ washing, cleaning and painting (O/S paint) |  |  |  | 858 |  | 858 |  |  | 0 | 0 | 0%
| Shipyard | If there is more than one grating for every sea chest (for each additional grating) |  |  |  | 221 |  | 221 |  |  | 0 | 0 | 0%
5.5 | Shipyard | Dismantle & refit bow thruster tunnel gratings, clean, blast, paint |  |  |  | 561.6 |  | 561.6 |  |  | 0 | 0 | 0%
| Shipyard | Polishing of bow thruster propeller |  |  |  | 644.8 |  | 644.8 |  |  | 0 | 0 | 0%
| Shipyard | Bow thruster overhaul with O/S spares |  |  |  | 8840 |  | 8840 |  |  | 0 | 0 | 0%
5.5.1 | Shipyard | Dismantle & refit stern thruster tunnel gratings, clean, blast, paint |  |  |  | 494 |  | 494 |  |  | 0 | 0 | 0%
| Shipyard | Polishing of stern thruster propeller |  |  |  | 572 |  | 572 |  |  | 0 | 0 | 0%
| Shipyard | Stern thruster overhaul with O/S spares |  |  |  | 7800 |  | 7800 |  |  | 0 | 0 | 0%
5.6 | Shipyard | Load test of E/R crane (SWL 2 MT) |  |  |  | 520 |  | 520 |  |  | 0 | 0 | 0%
5.7 | Shipyard | M/E air cooler - open end covers, chemical clean/wash, hydro test, reclose |  |  |  | 2496 |  | 2496 |  |  | 0 | 0 | 0%
5.9 | Shipyard | ME L.O cooler - remove, chemical clean plates, renew gaskets, test, refit |  |  |  | 6292 |  | 6292 |  |  | 0 | 0 | 0%
| Shipyard | LT coolers - remove, chemical clean plates, renew gaskets, test, refit |  |  |  | 16952 |  | 16952 |  |  | 0 | 0 | 0%
| Shipyard | ME HT cooler - remove, chemical clean plates, renew gaskets, test, refit |  |  |  | 5200 |  | 5200 |  |  | 0 | 0 | 0%
5.10 | Shipyard | Heater (M/E jacket preheater, tube type) - Not quoted in shipyard offer |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
5.11 | Shipyard | No.HFO SETT - 65,3 m³ |  |  |  | 1144 |  | 1144 |  |  | 0 | 0 | 0%
| Shipyard | Day Tank-20,2 m³ |  |  |  | 491.4 |  | 491.4 |  |  | 0 | 0 | 0%
| Shipyard | FO No3 C - 91,4 m³ |  |  |  | 1144 |  | 1144 |  |  | 0 | 0 | 0%
| Shipyard | FO No4/5 C 80,1 m³ |  |  |  | 1144 |  | 1144 |  |  | 0 | 0 | 0%
| Shipyard | FO No2 P- 154,5 m³ |  |  |  | 1767.48 |  | 1767.48 |  |  | 0 | 0 | 0%
| Shipyard | FO No2 S- 171 m³ |  |  |  | 1956.24 |  | 1956.24 |  |  | 0 | 0 | 0%
| Shipyard | FO No1 S- 112.09 m³ |  |  |  | 1282.3096 |  | 1282.3096 |  |  | 0 | 0 | 0%
| Shipyard | FO No2 S- 115.82 m³ |  |  |  | 1324.9808 |  | 1324.9808 |  |  | 0 | 0 | 0%
| Shipyard | SLUDGE TANK - 32,9 m³ |  |  |  | 1260 |  | 1260 |  |  | 0 | 0 | 0%
| Shipyard | OILY BILGE TANK - 10,7 m³ |  |  |  | 1260 |  | 1260 |  |  | 0 | 0 | 0%
5.12 | Shipyard | Aux. boiler - open door & side access door for inspection, cleaning, close up |  |  |  | 7488 |  | 7488 |  |  | 0 | 0 | 0%
| Shipyard | Aux. boiler - safety valve overhaul |  |  |  | 821.6 |  | 821.6 |  |  | 0 | 0 | 0%
5.13 | Shipyard | Main cooling S.W pump - 340 m3/h |  |  |  | 1674.4 |  | 1674.4 |  |  | 0 | 0 | 0%
| Shipyard | F.W.G ejector pump - 56 m3/h |  |  |  | 508.3 |  | 508.3 |  |  | 0 | 0 | 0%
5.14 | Shipyard | E/R overboard valve - butterfly/gate/storm overhaul in situ |  |  |  | 3009.6 |  | 3009.6 |  |  | 0 | 0 | 0%
| Shipyard | E/R overboard valve renewal with O/S valve - 3 pcs - 130 mm |  |  |  | 57.2 |  | 57.2 |  |  | 0 | 0 | 0%
5.15 | Shipyard | E/R valve - butterfly/gate/storm overhaul in situ (Estimated 2060 mm) |  |  |  | 1812.8 |  | 1812.8 |  |  | 0 | 0 | 0%
5.16 | Shipyard | Sewage line in E/R - DN 50 (2") SCH40 galvanized |  |  |  | 74.16 |  | 74.16 |  |  | 0 | 0 | 0%
| Shipyard | Sewage line in E/R - PN type flange DN 50 |  |  |  | 37.08 |  | 37.08 |  |  | 0 | 0 | 0%
| Shipyard | Sewage line in E/R - Elbow DN 50 |  |  |  | 74.16 |  | 74.16 |  |  | 0 | 0 | 0%
| Shipyard | Sewage line in steering gear - DN 50 (2") SCH40 galvanized |  |  |  | 92.7 |  | 92.7 |  |  | 0 | 0 | 0%
| Shipyard | Sewage line in steering gear - PN type flange DN 50 |  |  |  | 92.7 |  | 92.7 |  |  | 0 | 0 | 0%
| Shipyard | Sewage line in steering gear - Elbow DN 50 |  |  |  | 148.32 |  | 148.32 |  |  | 0 | 0 | 0%
| Shipyard | Sea water cooler inlet - DN 200 SCH80 galvanized |  |  |  | 259.74 |  | 259.74 |  |  | 0 | 0 | 0%
| Shipyard | Sea water cooler inlet - PN type flange DN 200 |  |  |  | 259.74 |  | 259.74 |  |  | 0 | 0 | 0%
| Shipyard | Sea water cooler outlet - DN 200 SCH80 galvanized |  |  |  | 259.74 |  | 259.74 |  |  | 0 | 0 | 0%
| Shipyard | Sea water cooler outlet - PN type flange DN 200 |  |  |  | 259.74 |  | 259.74 |  |  | 0 | 0 | 0%
5.20 | Shipyard | Main air reservoir survey - open manhole, clean, close (Q'ty 2) |  |  |  | 884 |  | 884 |  |  | 0 | 0 | 0%
| Shipyard | Aux/emergency air reservoir survey - open manhole, clean, close (Q'ty 1) |  |  |  | 338 |  | 338 |  |  | 0 | 0 | 0%
| Shipyard | Air receiver safety valve overhaul |  |  |  | 1747.2 |  | 1747.2 |  |  | 0 | 0 | 0%
5.27 | Shipyard | Steering gear hydraulic cylinders (2 pcs) OH with Owner spares |  |  |  | 6500 |  | 6500 |  |  | 0 | 0 | 0%
5.28 | Shipyard | Steering gear hydraulic pump OH with Owner spares |  |  |  | 7800 |  | 7800 |  |  | 0 | 0 | 0%
5.28 | Shipyard | Steering gear hydraulic control block OH with Owner spares |  |  |  | 3536 |  | 3536 |  |  | 0 | 0 | 0%
5.32 | Shipyard | Sewage treatment plant - thoroughly cleaned and ventilated |  |  |  | 1352 |  | 1352 |  |  | 0 | 0 | 0%
| Shipyard | Sewage treatment plant - chambers coated O/S paint and leakage test |  |  |  | 936 |  | 936 |  |  | 0 | 0 | 0%
6.1 | Shipyard | Electric motor overhaul tariff - up to 6kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 6-11kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 12-22kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 23-36kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 37-41kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 42-53kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 54-66kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 67-85kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 86-100kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 101-125kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 126-150kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 151-200kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - 201-300kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
| Shipyard | Electric motor overhaul tariff - more than 300kW |  |  |  | 0 |  | 0 |  |  | 0 | 0 | 0%
6.2 | Shipyard | Main L.O pump motor overhaul |  |  |  | 1440.4 |  | 1440.4 |  |  | 0 | 0 | 0%
| Shipyard | ER fan no.1 and no.2 - 36 kw motor overhaul |  |  |  | 1086.8 |  | 1086.8 |  |  | 0 | 0 | 0%
| Shipyard | ER fan 36kw - fan motors 60% extra |  |  |  | 652.08 |  | 652.08 |  |  | 0 | 0 | 0%
| Shipyard | ER fan 36kw - impeller dynamic balance 30% extra |  |  |  | 326.04 |  | 326.04 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.1 - 1.5kw motor overhaul |  |  |  | 2745.6 |  | 2745.6 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.1 - fan motors 60% extra |  |  |  | 1647.36 |  | 1647.36 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.1 - impeller dynamic balance 30% extra |  |  |  | 823.68 |  | 823.68 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.2 - 4 kw motor overhaul |  |  |  | 686.4 |  | 686.4 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.2 - fan motors 60% extra |  |  |  | 411.84 |  | 411.84 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.2 - impeller dynamic balance 30% extra |  |  |  | 205.92 |  | 205.92 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.3 - 7.5 kw motor overhaul |  |  |  | 915.2 |  | 915.2 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.3 - fan motors 60% extra |  |  |  | 549.12 |  | 549.12 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.3 - impeller dynamic balance 30% extra |  |  |  | 274.56 |  | 274.56 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.4 - 7.5 kw motor overhaul |  |  |  | 915.2 |  | 915.2 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.4 - fan motors 60% extra |  |  |  | 549.12 |  | 549.12 |  |  | 0 | 0 | 0%
| Shipyard | CH fan no.4 - impeller dynamic balance 30% extra |  |  |  | 274.56 |  | 274.56 |  |  | 0 | 0 | 0%
6.3 | Shipyard | ICCP - scaffolding outside of vessel |  |  |  | 2340 |  | 2340 |  |  | 0 | 0 | 0%
6.4 | Shipyard | Main switch board - clean & retighten connections |  |  |  | 858 |  | 858 |  |  | 0 | 0 | 0%
| Shipyard | Emergency switch board - clean & retighten connections |  |  |  | 650 |  | 650 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
[8 empty] | 0 |  |  | 0 | 0 | 0%
Formulas:
Total duration = DATEDIF([Start date],[End Date],"d")
Progress days = MIN(DATEDIF([Start date], L4, "d"), [Total duration])

## Class item
Class item
No. | Finding list | Description | Action plan / Result | Rectification by | Open date | Completion
1 | Sounding Pipe Vent Cock Stuck | Stuck vent cocks on self-closing sounding pipes with air vents were identified | Replacement is planned after material supply. | Crew | 30th April
2 | STP Manhole Cover Bolt Damage | Repair has been scheduled following your finding | Cleaning of the STP and bolt replacement are planned for 3 May. | Shipyard | 30th April
3 | Hot Water Boiler Safety Valve Hose | Found Temporary Hose | The temporary hose has been removed and will be replaced with a permanent (fixed) pipe | Crew | 30th April | 30th April
4 | Leak Traces on STP Top ER Pipe | Leakage sign has been found | Painting pipe is necesasry | Crew | 30th April
5 | Improper Paint Storage in E/R | All paints moved to be stored in the designated paint store. | The temporary wooden paint storage space will be dismantled on 3 May, considering hot work restrictions due to open E/R oil tanks. | Shipyard | 30th April
6 | Improper MGO Tank Drain Valve | A ball valve was found instead of a self-closing valve | This is assumed to be an unauthorized modification. Replacement is planned after self-closing valve supply. | Crew | 30th April
7 | Improper Securing of Heavy Items | Heavy equipment such as refrigerant cylinders, pipes, large valves, and M/E spares were found unsecured | These items have been relocated to a secured storage area in the spare room. | Crew | 30th April | 30th April
8 | Unapproved Receptacle Installation | The unauthorized receptacle, likely related to a dosing unit no longer in use, has been removed along with the dosing unit | Removed | Crew | 30th April | 30th April
9 | Unknown Battery in E/R |  | Confirmed to be A/E and Emergency G/E starting batteries. | Crew | 30th April | 30th April
10 | Purifier Room Flame Detector Foundation | Foundation has been damaged. | The damaged foundation has been repaired. | Crew | 30th April | 30th April
11 | A/E F.O. Inlet Line Isolation Valve Issue (Non-compliance with SOLAS Regulation) | Please refer to the requirements of SOLAS. CH.II-2,Reg.4 section 2.2.5.5 which was attached, to confirm the arrangement of Fuel Isolating valve of Generator engine No.1 and No.2 | a. Firstly, we are currently confirming with the engine maker whether FOV33 (solenoid valve) is capable of being closed via a remote activation system (e.g., remote push-button). : Awaiting for Maker's response. (1st May) b. If the valve does not operate remote button, we plan to discuss the required line modification with BV Korea, obtain drawing approval, and proceed with modification in accordance with SOLAS Chapter II-2, Regulation 4, Section 2.2.5.5. | Shipyard | 30th April
12 | Cargo hold Ventilation Mesh Cover #3 C/H AFT | Mesh cover has been broken | Will discuss repair plan with shipyard. | Shipyard | 1st May
13 | #3 FWD C/H Explosion-proof light | #3 FWD C/H Explosion-proof light is missing | Spare to be supplied and replaced. | Crew | 1st May
14 | #2 C/H Ventilation Mesh Cover | Mesh cover has been broken | Will discuss repair plan with shipyard. | Shipyard | 1st May
15 | Foremast Light fixture | The support for the foremast light is missing, and associated cable arrangement is improperly installed. | Will discuss repair plan with shipyard. | Shipyard | 1st May
16 | Provision store ventilation cover | Cover has been broken. | Will discuss repair plan with shipyard. | Shipyard | 1st May
17 | Duct Fire damper (Bridge) | As the damper is installed at a high position, it is difficult to operate manually. Please install a wire mechanism to allow remote opening and closing. | Wire to be installed with handle for each fire damper | Crew | 1st May
18 | Air horn foundation (Monkey island) | Air horn foundation is in rusty condition | De-rusted & Painted | Crew | 1st May | 1st May
19 | Bridge Wooden Structures | The sheet covering on the wooden structure in the bridge has peeled off. | Will discuss repair plan with shipyard. | Shipyard | 1st May
20 | Lashing Bridge (#3 C/H AFT) Light Fixture | 1 Set of Light fixture is missing. | Spare to be supplied and replaced. | Crew | 1st May
21 | Reefer Socket Box | Several reefer socket caps have been found missing, and the existing ones are not closing securely. | Spare to be supplied and replaced. | Crew | 1st May
22 | #3 Cargo hold Fan | Foundation is in rusty condition | De-rusted & Painted | Crew | 1st May | 1st May
23 | Cable Penetration | Some deck cable penetrations were found not to be properly sealed. | Proper sealing compound to be applied. | Crew | 1st May
24 | HFO storage tank (P) Manhole cover | Found leakage trace. | Re-tighted manhole and Removed oil tracing. Re-painted | Crew | 1st May | 1st May
25 | Railing Door of life raft (Stbd) | Need to Free-up, de-rust, and paint | Job to be planned | Crew | 1st May
26 | Em'cy lights of Accommodation | Defects were identified in six emergency lights located around the accommodation area, including issues with their supporting structures. | Em'cy light spare to be supplied and replaced, while the replacement of the supports to be discussed with the shipyard. | Crew / Shipyard | 1st May
27 | Fire hose box (Deck B) | Box door has been broken. | Replaced by new box | Crew | 1st May
28 | Soud Pipe (Monkey Island) | Rusty condition | Pipe to be replaced | Shipyard | 1st May
29 | Loading computer program certificate | Cert is missing | Found and provided to Class Surveyor. (Maker contact) | Crew | 1st May | 2nd May
30 | BWTS calibration period to be clarifed | With Panasia
31 | SE | VDR만 남음 | 5/13 VDR retrofitting 후
32 | MAK engine 관련 Technical circular | 받음
33 | 이전 UWI report
34
35
36